## CIP List
Priority Project List Approval Date: | Updated September 15, 2025 (Ross Pike)
Contact Name: | Roy Moosa is Mobility contact
Contact Tel: | 760-723-1181
Contact Email: | roymoosacalifornia@gmail.com
Project Manager: | Cynthia Curtis, DPW Capital Improvements Program
Contact Tel: | 619-981-6294
2026 Fallbrook Community Planning Group Capital Improvement Project Proposed Priority List
Priority / Status | Project Type * | Project Name, Description, and Limits | Recommended By: | Notes
1 | Traffic Safety/Signals | Illuminated crosswalk at S Mission and Elder – FLASHING LIGHT CROSSWALK | Circulation Committee
2 | Traffic Safety/Signals | Stoplight at Fallbrook Street and Morro Rd (New Village View County Park entrance) - Asking County to change from RRFB to stoplight, MAJOR safety concerns | Circulation Committee | Moved up from #11 to #2 in 2025
3 | Sidewalks | Path/trail on S Stage Coach Ln from High School Admin Building to Reche Road | Circulation Committee
4 | Sidewalks | East Mission: Iowa to Brandon (preferably the south side of E Mission) | Circulation Committee
5 | Sidewalks | South Mission: Fig to Elder | Circulation Committee
6 | Sidewalks | East Mission: Main to Iowa | Circulation Committee
7 | Traffic Safety/Signals | Crosswalk at Ammunition and Main (near Del Rey Avocado Company at the Shell Station) – FLASHING LIGHT CROSSWALK | Private Citizen
8 | Traffic Safety/Signals | Crosswalk at S Mission Rd and Fig – FLASHING LIGHT CROSSWALK | Circulation Committee
9 | Traffic Safety/Signals | Crosswalk at Aviation and Main – FLASHING LIGHT CROSSWALK | Private Citizen
10 | Traffic Safety/Signals | Crosswalk at Alvarado and Main – FLASHING LIGHT CROSSWALK | Private Citizen
11 | Traffic Safety/Signals | Reflective phosphorescent paint on all crosswalk intersections on Main (create crosswalks where none exist) | Circulation Committee
12 | Drainage | E Mission and Brandon Flooding | Circulation Committee
13 | Intersections | S Mission and Ammunition: Second left turn lane once you've turned right from Main Ave | Circulation Committee
14 | Sidewalks | Sidewalks on West Clemmens | Private Citizen
15 | Traffic Safety/Signals | Crosswalk by park at West Clemmens | Private Citizen
16 | Traffic Safety/Signals | Sidewalks on West Clemmens so sidewalks are unobstructed parking spots for pedestrians | Private Citizen
17 | Road Reconfiguration | East Mission: Increase left turn lane, and left turn lanes at side roads, and resurface at 395 and I-15 | Circulation Committee
18 | Road Reconfiguration | East Mission left turn lanes at side roads (into neighborhoods and private drives) from Hamilton to the 15 freeway. | Circulation Committee | Added Hamilton to Fwy in 2025
19 | Road Reconfiguration | Stagecoach @ Reche Rd: If driving north, Add an actual Right turn lane towards Potter Junior High (people use bikepath) | Circulation Committee
20 | Traffic Safety/Signals | Crosswalk at Brandon and east Mission – FLASHING LIGHT CROSSWALK | Circulation Committee
21 | Road Reconstruction | Rocky Crest Road repairs. It is a safety hazard. Even though this road may be private, the public uses it more than the private road owners. | Planning Group
22 | Road Reconstruction | South Mission: potholes and cracking throughout | Circulation Committee
23 | Drainage | North Wisconsin and West Hawthorne | Circulation Committee
24 | Traffic Safety/Signals | Speed limit painted on street at West Clemmens | Private Citizen
25 | Bike Lanes | @ Reche Road, @South Mission, @ Olive Hill | Circulation Committee
26 | Road Reconfiguration | East Mission and Live Oak: It is difficult to turn during peak traffic. Road reconfiguation is needed to improve traffic flow. | Circulation Committee | NEW 2026
27 | Sidewalks | Continuation of sidewalk adjacent to The Village View Park along Morro Road. | Circulation Committee | New 2026
DEFER TO REVIT COMM | Traffic Safety/Signals | Bulb outs on Main at Elder and Ivy or Hawthorne – DEFER TO REVITALIZATION COMMITTEE AS PART OF DOWNTOWN REVITALIZATION PROJECT | Chamber & FVA
DEFER TO REVIT COMM | Road Reconstruction | Main Avenue potholes and cracking throughout. – DEFER TO REVITALIZATION COMMITTEE AS PART OF DOWNTOWN REVITALIZATION PROJECT | Circulation Committee
DEFER TO REVIT COMM | Traffic Safety/Signals | Crosswalks on Main – DEFER TO REVITALIZATION COMMITTEE AS PART OF DOWNTOWN REVITALIZATION PROJECT | Circulation Committee
APPROVED/PENDING | Traffic Safety/Signals | Santa Margarita and Mission | Circulation Committee
DONE | Sidewalks | Sidewalk from Library to Mission Rd | Planning Group
DONE | Traffic Safety/Signals | Green Canyon and South Mission: if no traffic light, then a flashing light at Green Cyn | Circulation Committee
DONE | Road Reconfiguration | Reche Road: Add left turn lanes by Potter Junior High, and Live Oak School | Circulation Committee
ELIMINATE | Intersections | Stagecoach past Morrow: check for safety | Circulation Committee
ELIMINATE | Intersections | Via Monserate and Mission: less sharp turn | Circulation Committee
REQUEST REVIEW | Traffic Safety/Signals | Crosswalk across Mission Rd at Old Stage Road | Planning Group
REQUEST REVIEW | Sidewalks | Sidewalk along Old Stage Road from Mission Rd to Fallbrook Street | Planning Group
REQUEST REVIEW | Traffic Safety/Signals | Flashing yellow light at South Mission and Peppertree Lane | Circulation Committee
REQUEST REVIEW | Traffic Safety/Signals | East Mission (from Stage Coach to Live Oak) Traffic Safety: Increased Signage for speed, turn lanes, | Circulation Committee | NEW 2025
REQUEST REVIEW | Road Reconstruction | Avenida Campana resurfacing | Private Citizen | NEW 2025
Priority Number | * Project type selections | Project Name, Description, and Limits | Recommended By?
Prioritize your projects by importance. Which ones you would like constructed first. | Road Reconstruction/New Roads | Give the project a name: ex. Alpine and Tavern Intersection Improvements | Who recommended the project.
| Sidewalk/Pathways | Describe the improvements required: New continental crosswalks at all 4 corners. | Ex. 3 local business owners have requested the project due to multiple patrons who have almost been hit by cars while crossing the intersection.
| Drainage | New ADA compliant ramps at all 4 corners. Add left hand turn lane on Tavern turning east Alpine.
| Traffic Signals | Limits: ex. 100 feet east, west, north and south of the intersection of Alpine Blvd and Tavern Rd.
Intersections
Bridges
Bicycles